## Task_Table
| Rembler Software - Reversi Game |  |  | as of: | 2017-11-30
[7 empty] | 2017-09-04 | [6 empty] | 2017-09-11 | [6 empty] | 2017-09-18 | [6 empty] | 2017-09-25 | [6 empty] | 2017-10-02 | [6 empty] | 2017-10-09 | [6 empty] | 2017-10-16 | [6 empty] | 2017-10-23 | [6 empty] | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13 | [6 empty] | 2017-11-20 | [6 empty] | 2017-11-27
ID | Task Name | Duration | Start | Finish | Predecessors | Resource Name | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Begin group project | 1 day | Mon 9/4/17 | Mon 9/4/17 |  | All | bar: 2017-09-04 M
2 | Team Project Information Due | 1 day | Mon 9/4/17 | Mon 9/4/17 | 1 | All | bar: 2017-09-04 M
3 | Preliminary Game Concept Research | 7 days | Mon 9/4/17 | Mon 9/10/17 | 2 | All | bar: 2017-09-04 M to 2017-09-11 S
4 | Preliminary Logic Implementation Research | 7 days | Mon 9/11/17 | Sun 9/17/17 | 2,3 | All | bar: 2017-09-11 M to 2017-09-18 S
5 | Preliminary Programming Algorithm Research | 7 days | Mon 9/18/17 | Sun 9/24/17 | 2,3,4 | All | bar: 2017-09-18 M to 2017-09-25 S
6 | Team Meeting: Initial Research Review | 1 day | Sun 9/24/17 | Sun 9/24/17 | 2,3,4 | All | bar: 2017-09-25 S
7 | Additional Game Concept Research | 7 days | Mon 9/25/17 | Sun 10/01/17 | 6 | All | bar: 2017-09-25 M to 2017-10-02 S
8 | Additional Logic Implementation Research | 7 days | Mon 10/2/17 | Sun 10/8/17 | 6 | All | bar: 2017-10-02 M to 2017-10-09 S
9 | Additional Programming Algorithm Research | 7 days | Mon 10/9/17 | Sun 10/15/17 | 6 | All | bar: 2017-10-09 M to 2017-10-16 S
10 | Team Meeting: Finalize Research Points | 1 day | Sun 10/15/17 | Sun 10/15/17 | 7,8,9 | All | bar: 2017-10-16 S
11 | Project checkpoint Due | 1 day | Thu 10/19/17 | Thu 10/19/17 | 10 | All | bar: 2017-10-16 T
12 | Game logic research | 7 days | Mon 10/16/17 | Sun 10/22/17 | 10 | All | bar: 2017-10-16 M to 2017-10-23 S
13 | Team Meeting: Logic design decision | 1 day | Sun 10/22/17 | Sun 10/22/17 | 12 | All | bar: 2017-10-23 S
14 | Pseudocode development | 7 days | Mon 10/23/17 | Sun 10/29/17 | 13 | All | bar: 2017-10-23 M to 2017-10-30 S
15 | Team Meeting: Pseudocode decision | 1 day | Sun 10/29/17 | Sun 10/29/17 | 14 | All | bar: 2017-10-30 S
16 | Coding Turn Switch and Valid Move Module | 7 days | Mon 10/30/17 | Sun 11/05/17 | 15 | Tung Duc Vu | bar: 2017-10-30 M to 2017-11-06 S
17 | Coding Valid Move and Difficulty Module | 7 days | Mon 10/30/17 | Sun 11/05/17 | 15 | Lan Vu | bar: 2017-10-30 M to 2017-11-06 S
18 | Coding Draw Board Module | 7 days | Mon 10/30/17 | Sun 11/05/17 | 15 | Keyur Savjani | bar: 2017-10-30 M to 2017-11-06 S
19 | Coding Update Array Module | 7 days | Mon 10/30/17 | Sun 11/05/17 | 15 | Roman Chernov | bar: 2017-10-30 M to 2017-11-06 S
20 | Team Meeting: Code review and adjustment | 1 day | Sun 11/05/17 | Sun 11/05/17 | 16,17,18,19 | All | bar: 2017-11-06 S
21 | Coding Module, adjustment implementation | 7 days | Mon 11/06/17 | Sun 11/12/17 | 20 | Tung Duc Vu | bar: 2017-11-06 M to 2017-11-13 S
22 | Coding Module, adjustment implementation | 7 days | Mon 11/06/17 | Sun 11/12/17 | 20 | Lan Vu | bar: 2017-11-06 M to 2017-11-13 S
23 | Coding Module, adjustment implementation | 7 days | Mon 11/06/17 | Sun 11/12/17 | 20 | Keyur Savjani | bar: 2017-11-06 M to 2017-11-13 S
24 | Coding Module, adjustment implementation | 7 days | Mon 11/06/17 | Sun 11/12/17 | 20 | Roman Chernov | bar: 2017-11-06 M to 2017-11-13 S
25 | Team Meeting: Review and adjustment, debug | 1 day | Sun 11/12/17 | Sun 11/12/17 | 21,22,23,24 | All | bar: 2017-11-13 S
26 | Coding board letters and numbers | 7 days | Mon 11/13/17 | Sun 11/19/17 | 25 | Tung Duc Vu | bar: 2017-11-13 M to 2017-11-20 S
27 | Coding 2 players and difficulty algorithm | 7 days | Mon 11/13/17 | Sun 11/19/17 | 25 | Lan Vu | bar: 2017-11-13 M to 2017-11-20 S
28 | Coding Error Explanation | 7 days | Mon 11/13/17 | Sun 11/19/17 | 25 | Keyur Savjani | bar: 2017-11-13 M to 2017-11-20 S
29 | Coding Sounds | 7 days | Mon 11/13/17 | Sun 11/19/17 | 25 | Roman Chernov | bar: 2017-11-13 M to 2017-11-20 S
30 | Team Meeting: Extra features | 1 day | Sun 11/19/17 | Sun 11/19/17 | 26,27,28,29 | All | bar: 2017-11-20 S
31 | Code improvements | 7 days | Mon 11/20/17 | Sun 11/26/17 | 30 | Tung Duc Vu | bar: 2017-11-20 M to 2017-11-27 S
32 | Code improvements | 7 days | Mon 11/20/17 | Sun 11/26/17 | 30 | Lan Vu | bar: 2017-11-20 M to 2017-11-27 S
33 | Coding Statistical output | 7 days | Mon 11/20/17 | Sun 11/26/17 | 30 | Keyur Savjani | bar: 2017-11-20 M to 2017-11-27 S
34 | Creating documentarian | 7 days | Mon 11/20/17 | Sun 11/26/17 | 30 | Roman Chernov | bar: 2017-11-20 M to 2017-11-27 S
35 | Team Meeting: Testing and documentation | 5 days | Sun 11/26/17 | Thu 11/30/17 | 31,32,33,34 | All | bar: 2017-11-27 S to 2017-11-27 T
36 | Completed project due on e-Learning | 1 day | Thu 11/30/17 | Thu 11/30/17 | 35 | All | bar: 2017-11-27 T
Notes:
09/24 - Team meeting about initial research of all topics, making sure everyone is on the same page with information and ideas.
10/15 - Team meeting. We have difficulties deciding on a computer logic we want to utilize. We discussed pros and cons for different possible tactics for the next move algorithm. We also discussed a difficulty level implementation for the game.
10/22 - Logic design setteled.
10/29 - Pseudocode is designed.
11/05 - Main modules review. Put modules together.
11/12 - Extra features discussion and selection.
11/19 - Adjustments made to the statistical module.
11/28 - Final corrections.
Team Members:
| Tung Duc Vu | tdv160130
| Lan Vu | lxv160330
| Keyur Savjani | kss160430
| Roman Chernov | rvc150030